## Summary
Open Defect Report
Tags: VS3, MCIS, R4.5, R4.4.1 (issue matches ANY tag)
Generated: 2026-10-15 08:58 UTC
Total open defects: 23
JQL:
((labels = "VS3" OR component = "VS3") OR (labels = "MCIS" OR component = "MCIS") OR (labels = "R4.5" OR fixVersion = "R4.5" OR affectedVersion = "R4.5") OR (labels = "R4.4.1" OR fixVersion = "R4.4.1")) AND issuetype in ("Bug") AND statusCategory != Done ORDER BY priority DESC, created ASC
Defects by tag
Value | Count | % of total
VS3 | 2 | 8.696%
MCIS | 5 | 21.74%
R4.5 | 13 | 56.52%
R4.4.1 | 3 | 13.04%
Defects by status
Value | Count | % of total
Code Review | 6 | 26.09%
In Development | 5 | 21.74%
In QA | 5 | 21.74%
New | 4 | 17.39%
Ready for Sprint | 1 | 4.348%
SME Review | 1 | 4.348%
Triaged | 1 | 4.348%
Defects by priority
Value | Count | % of total
Medium | 12 | 52.17%
High | 8 | 34.78%
Low | 3 | 13.04%
Defects by project
Value | Count | % of total
SD-WAN | 17 | 73.91%
Pandora | 5 | 21.74%
Quality Engineering - Global Ground Network Systems | 1 | 4.348%
Defects by age
Value | Count | % of total
0-7 days | 5 | 21.74%
8-30 days | 9 | 39.13%
31-90 days | 5 | 21.74%
91-180 days | 1 | 4.348%
180+ days | 3 | 13.04%
Defects by assignee (top 20)
Value | Count | % of total
Holder, Joe | 6 | 26.09%
Unassigned | 4 | 17.39%
Vailamur Nagarajan, Koushal | 4 | 17.39%
Smith, Nick | 3 | 13.04%
Giskegjerde, Trond Vidar | 1 | 4.348%
Klemetsen, Lene Mari | 1 | 4.348%
McGuinness, Jack | 1 | 4.348%
Norris, Oliver | 1 | 4.348%
Radu, George (Contractor) | 1 | 4.348%
Shrewsbury, Federico | 1 | 4.348%

## Open Defects
Key | Summary | Description | Type | Status | Status Category | Priority | Matched Tags | Project | Assignee | Reporter | Created | Updated | Age (days) | Days Since Update | Due Date | Labels | Components | Fix Versions | Affects Versions | Parent | URL
SDWAN-13229 | MCIS, AISM Ubuntu VM requires reboot to enable VLAN20 | The Ubuntu version of the AISM VM is setup with vlan201 as default. When MICS is activated, VLAN201 is removed from the network interface file, and VLAN20 is added. But the change is not automatically applied. To get it working, it's required to manually reboot the AISM VM to get CrewHub service working. The Value added services projects do not have any tasks for doing this, and in my opinion, adding a task for doing a reboot is not the way to go when we want processes to be automated as much as possible. I assume there is a script or playbook pulling config from shore. Wouldn't it be able to detect interface changes and reboot the service if any changes are detected? | Bug | Code Review | In Progress | High | MCIS | SD-WAN | Holder, Joe | Giskegjerde, Trond Vidar | 2026-08-26 04:16 | 2026-09-17 06:45 | 49 | 27 |  | MCIS |  | 26.3 | NA |  | https://jira.viasat.com/browse/SDWAN-13229
SDWAN-13329 | hosting_manager: VM_NAME_TO_SDS_HOST still maps to 'mcis-aism' after SDWAN-13107 — running-version MDF never published | h3. Symptom hosting_manager was missed in the SDWAN-13107 rename sweep: {{api/app/endpoints.py:177}} still maps the agent-reported image name onto the retired trial host key {{mcis-aism}}. Consequently {{/v1/notify}} resolves no service for an AISM running-version report and skips the {{hosting-service-status-received}} MDF publish, warning-logged only. *Scope of impact, stated precisely:* * *No shore service consumes this message.* Grepped every repo in the Repos index — the only consumer is the SI harness. Nothing in production is degraded by it. * *SI_654's running-version scenario should be failing.* {{SI_654_mcis_coverage.feature:56}} binds a watcher and expects the MDF within 15 minutes, then asserts {{the reported host in the MDF message is "aism"}}. With nothing published that step times out. *Not yet run* — this is deduced from the code, and it is the check that would confirm or refute the whole diagnosis. If that scenario has been green since #171 merged, the diagnosis is... | Bug | Code Review | In Progress | High | MCIS | SD-WAN | Holder, Joe | Holder, Joe | 2026-09-09 02:13 | 2026-09-09 03:06 | 35 | 35 |  | PI-26.3-Planned-Committed, Value_adds_and_service_customisation | MCIS | 26.3 | 26.3 |  | https://jira.viasat.com/browse/SDWAN-13329
SDWAN-13395 | Geo-Fencing SNAPI Interface unstable | It seems snapi interface is not as stable as it used to be. The snapi calls are synchronous and are intertwined with async code. My hunch is that when we retry to connect to SNAPI everything waits for that to finish. It also happens in dev, CI tests are failing randomly because of this if I remember correctly from the last time I checked with Dinu | Bug | In Development | In Progress | High | R4.5 | SD-WAN | Radu, George (Contractor) | Holder, Joe | 2026-09-15 07:21 | 2026-10-07 01:08 | 29 | 8 |  | R4.5 |  | 26.3, R4.5 | 26.3 |  | https://jira.viasat.com/browse/SDWAN-13395
SDWAN-13436 | VS3 ACU assurance data check is incorrect | When we first developed against the Intellian VS60, we only had a simulator to work with to get assurance data, and there is a check in the code to validate metrics before we can save them to disk. We took this code out but when doing so, the underlying logic was wrong. | Bug | In QA | In Progress | High | R4.4.1 | SD-WAN | Smith, Nick | Smith, Nick | 2026-09-18 03:22 | 2026-10-07 00:34 | 26 | 8 |  | R4.4.1, VS3-Beta |  | r4.4.1 | R4.4 |  | https://jira.viasat.com/browse/SDWAN-13436
SDWAN-13584 | sdwan-seed-generator API container has no readiness/liveness probe - hung gunicorn worker went undetected for 2.5 days on dev | h3. Summary On dev, the sdwan-seed-generator REST API stopped serving at 2026-09-24 18:36 UTC and stayed that way until it was manually restarted on 2026-09-27 07:13 UTC. Kubernetes kept reporting the pod as 2/2 Running/Ready the whole time, because the {{sdwan-seed-generator-api}} container has no readiness or liveness probe. h3. Evidence * Pod {{sdwan-seed-generator-deployment-db5468c48-llqnq}}, created 18:33 UTC Thu as a replacement pod. The previous pod and a parameter-manager pod were left stuck Terminating on node ip-10-200-74-222, which suggests a node disruption. * gunicorn config: 1 worker, sync worker class, 1 thread, bind 0.0.0.0:80. The container log ends at "1 workers" and never shows "Booting worker with pid". Worker process 17 was alive but served nothing. * {{GET http://127.0.0.1:80/v1/seep/link-inventory/<sdp>}} run *inside the pod* timed out. From sdwan-activation-service, both the Service DNS name and the pod IP gave ConnectTimeout. * After {{kubectl rollout resta... | Bug | In QA | In Progress | High | R4.5 | SD-WAN | Holder, Joe | Holder, Joe | 2026-09-27 00:16 | 2026-10-05 07:45 | 18 | 9 |  | sdwan-seed-generator, slowtrack |  | 26.4 | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13584
DORA-6822 | Hosting will not start. | Vessel Name: Elandra Cypress Remote Site ID: 250100324550000 CNSID: QlqULO70mYK8d4u CCE Instance: 2 It seems to be affected [https://jira.viasat.com/browse/SDWAN-11528] and in additional crashed the environment. Have added the CPU shares again, they was missing int the conf.d and init.d file. Did also copy the whole conf.d file and init.d file from a working R4.4 system since the container version was the same, no effect. ( both old files are present as .bak {code:java} docker logs hosting exec /entrypoint.sh: exec format error {code} {code:java} drwxr-xr-x 2 root root 4096 Dec 11 2025 _data -rw------- 1 root root 101 Dec 11 2025 opts.json /var/lib/docker/volumes/hosting-var_images # cd _data/ /var/lib/docker/volumes/hosting-var_images/_data # ls -l total 0 {code} {code:java} sudo service hosting start hosting * Starting hosting ... * All interfaces are available: eth4 eth9 RTNETLINK answers: File exists RTNETLINK answers: File exists de790501a3e3e2376344929ad3534610f249e09ce385... | Bug | In Development | In Progress | High | R4.5 | Pandora | Vailamur Nagarajan, Koushal | Oien, Ole - Richard | 2026-09-29 01:21 | 2026-10-13 22:50 | 16 | 1 |  | Inlife, R4.5 |  | R4.5 |  |  | https://jira.viasat.com/browse/DORA-6822
DORA-6864 | Updater 1.0.78 cannot SSH to c5921, remote upgrade fails after reboot | *Problem* After the updater moved to Alpine 3.23 (fleet_edge_updater PR #177, updater 1.0.78), remote upgrades are marked FAILED after the edge reboots. The upgrade itself completes, but the updater's post-reboot "edge is fully up" check times out. Seen in Slow Track (build 2.16.512): SI-582 (pull remote upgrade) and SI-584 (two-stage remote upgrade). *Cause* The check SSHes from the updater container to each edge host, including c5921. The new image has OpenSSH 10.2, which no longer accepts the legacy SSH algorithms c5921 uses (ssh-rsa host key and RSA certificate login). The old image (OpenSSH 8.1) accepted them. {noformat}Unable to negotiate with 10.0.3.8 port 22: no matching host key type found. Their offer: ssh-rsa,ssh-dss{noformat} *Fix* Re-enable the legacy algorithms in the updater image for c5921 only (same options as the SI fix in SDWAN-12955): {noformat}HostKeyAlgorithms +ssh-rsa PubkeyAcceptedAlgorithms ssh-rsa-cert-v01@openssh.com,ssh-rsa{noformat} Verified manually on... | Bug | In Development | In Progress | High | R4.5 | Pandora | Vailamur Nagarajan, Koushal | Vailamur Nagarajan, Koushal | 2026-10-11 07:56 | 2026-10-11 20:17 | 3 | 3 |  | Inlife | edge-updater, remote-upgrade | R4.5 |  |  | https://jira.viasat.com/browse/DORA-6864
DORA-6868 | Updater 1.0.78 lacks Ansible collections: all_targets.yaml fails to load, so the remote upgrade fails 2 s after precache | h3. Problem Since updater 1.0.78 (fleet_edge_updater PR #177, DORA-6818: current moved to Alpine 3.23 / ansible-core 2.19), a remote upgrade fails on any edge that is running the new updater. Precache succeeds, then {{all_targets.yaml}} fails to load. About 2 seconds later the transaction goes to PLAYBOOK_EXECUTION_FAILED, with no task output and an empty reason. The image installs ansible-core (built-in modules only) plus {{community.docker}}. That covers {{precache_edge.yaml}} ({{docker_image}}), but fleet_edge_provisioning also uses modules from other collections: ¦¦Collection¦¦Modules used¦¦Effect¦¦ ¦community.general¦modprobe, lvg, lvol, filesystem, influxdb_database, influxdb_retention_policy¦all_targets.yaml fails to load (modprobe in roles/common/tasks/main.yaml:81)¦ ¦ansible.posix¦ansible.builtin.mount / mount (provision_network.yaml, provision_core.yaml)¦all_targets.yaml fails to load¦ ¦community.libvirt¦virt, virt_net (roles/libvirt, roles/vms/tasks/*_upgrade.yaml, cleanu... | Bug | In Development | In Progress | High | R4.5 | Pandora | Holder, Joe | Varatharajah, Gobeeshan | 2026-10-13 01:37 | 2026-10-13 07:41 | 2 | 1 |  | Inlife, claude-code-support |  | R4.5 |  |  | https://jira.viasat.com/browse/DORA-6868
SDWAN-9929 | Netmon monitoring of eth7 and eth8 doesn't work | Monitoring of eth7 and eth8 does not work. See error in log below. Also, if I shutdown eth7 and eth8 manually they will not be taken up by the netmon service again. For eth6 it works fine. Docker logs netmon: {noformat}* 2025-08-01 12:53:55 [ INFO ] [ state_machine.py (41)¦ state_machine - (Thread-1) ] :: State::process_state() * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (43)¦ state_machine - (Thread-1) ] :: State::process_state() state: NetmonState.ALL_INTERFACES_UP * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (70)¦ state_machine - (Thread-1) ] :: State::process_state() iterating managed interfaces: ['eth1', 'eth2', 'eth6', 'eth7, eth8'] * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (72)¦ state_machine - (Thread-1) ] :: State::process_state() checking if interface eth1 is down * 2025-08-01 12:53:55 [ INFO ] [ eth_handler.py (11)¦ eth_handler - (Thread-1) ] :: is_interface_down(eth1) False * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (72)¦ state... | Bug | Code Review | In Progress | Medium | R4.5 | SD-WAN | Holder, Joe | Giskegjerde, Trond Vidar | 2025-08-01 05:58 | 2026-10-07 08:53 | 439 | 7 |  | Inlife, R4.5 | netmon | 26.4 |  |  | https://jira.viasat.com/browse/SDWAN-9929
SDWAN-11453 | MCIS activation status in Pulse show success also when it failed | Issue found during MCIS integration testing. The MCIS activation status in Pulse only reflects if OMS are happy with the request or not. If it fails in AeroManager or SDWAN manager this is not shown anywhere. Due to this it will not be possible to see if MCIS activation is successful or not before the config is applied on the Edge and tested by customer. There must be an indication somewhere that MCIS activation has completed succesfully through all the involved systems. Preferrably in the status view for the MCIS activation in Pulse. !image-2025-12-05-15-50-51-810.png! | Bug | Triaged | To Do | Medium | MCIS | SD-WAN | Norris, Oliver | Giskegjerde, Trond Vidar | 2025-12-05 06:40 | 2026-06-02 01:45 | 313 | 135 |  | MCIS |  |  |  |  | https://jira.viasat.com/browse/SDWAN-11453
QEGNS-2 | VS3 Reflector Tie Rod Weld Failure – Butt Joint Separation at Sleeve | Field failures observed where reflector tie rod butt welds at the sleeve are cracking/separating, compromising reflector structural integrity. Original supplier (Global Skyware) is out of business. Norcar Satcom acquired IP and continues sourcing from the same China supplier. *Action:* Implement supplier quality controls and weld validation with Norcar Satcom prior to procuring replacement tie rods for field remediation. | Bug | SME Review | In Progress | Medium | VS3 | Quality Engineering - Global Ground Network Systems | McGuinness, Jack | McGuinness, Jack | 2026-02-16 10:10 | 2026-09-29 12:23 | 240 | 15 |  | VS3 |  |  |  |  | https://jira.viasat.com/browse/QEGNS-2
SDWAN-12614 | Submitting an invalid VS3 MAC address causes SDP order to get stuck and not allowing new order with corrected MAC | If you specify wrong MAC address in Pulse you will not get any notifications that it's wrong before "it's too late". SDP will try to provision the CDQ with the invalid MAC and attach this to the current CNS ID or Remote site ID. The SDP order get stuck in running state but also left in a state where it cannot be aborted, since it's already sent this to CDQ. This is what I see when checking the status in SDP web interface: !image-2026-06-04-10-58-35-678.png¦width=307,height=407! In Pulse I only see the order is "failed". This error message should have given an explanation of why it failed. We need to investigate what happened here. After correcting the MAC address, I re-submitted the provision VS3 request. Then I got this error: {code:java} Failed : One or more previous messages with ids ae30b916-fbce-4bed-8c72-203b129e4eaa related to site_id 127744 are still being handled. Please wait for them to complete and then try your request again. {code} If an invalid MAC address is specified... | Bug | In QA | In Progress | Medium | VS3 | SD-WAN | Shrewsbury, Federico | Giskegjerde, Trond Vidar | 2026-06-04 01:58 | 2026-08-20 03:30 | 133 | 55 |  | VS3 |  | PI 26.2, 26.3 | NA |  | https://jira.viasat.com/browse/SDWAN-12614
DORA-6764 | DORA-6751 follow-up: harden c5921 against analogous NIC identity/enumeration exposure | Follow-up to DORA-6751. The DORA-6751 fix (fleet_edge_provisioning PR [#1084¦https://github.com/Inmarsat/fleet_edge_provisioning/pull/1084], now merged) hardened the *network* and *core* VMs against the boot-time NIC-enumeration race by waiting for each MAC before {{nameif}}. It explicitly *descoped the c5921* ("Cisco IOS, different mechanism"). This ticket covers the c5921, which has an *analogous latent exposure* — and was in fact the variant seen on customer vessels in DORA-6751. h4. Correction to the original scoping note The c5921 is not a bare Cisco-IOS appliance. It is a KVM guest running a *CentOS/RHEL-family Linux* (uses {{/etc/sysconfig/network-scripts/ifcfg-*}}) that hosts the Cisco ESR software router as a userspace process. So it is Linux underneath and *does* have a NIC-identity story — just a different one from the Debian {{nameif}} VMs. h4. The exposure (code-grounded) Refs: {{fleet_edge_provisioning:roles/vms/templates/c5921/c5921.xml}}, {{roles/c5921/tasks/main.yam... | Bug | Ready for Sprint | To Do | Medium | R4.5 | Pandora | Holder, Joe | Holder, Joe | 2026-08-26 00:52 | 2026-08-26 03:58 | 50 | 49 |  | Inlife, R4.5 |  | PI 26.3 |  |  | https://jira.viasat.com/browse/DORA-6764
SDWAN-13444 | MCIS, Checkbox for manual FH deactivation not working | If Fleet Hotspot have been manually deactivated on a system, the checkbox for confirming this does not make any difference for MCIS. Even if ticked off it will display an error message about FH deprovision is required when I try to provision MCIS. !image-2026-09-18-16-06-59-753.png¦width=623,height=1490! | Bug | Code Review | In Progress | Medium | MCIS | SD-WAN | Giskegjerde, Trond Vidar | Giskegjerde, Trond Vidar | 2026-09-18 07:08 | 2026-10-08 01:28 | 26 | 7 |  | MCIS |  | PI 26.3 | NA |  | https://jira.viasat.com/browse/SDWAN-13444
SDWAN-13446 | MCIS, Crew size is hardcoded to 64 in OMS template | Currently, the crew size has been hardcoded to 64 in the MCIS template in OMS. Shouldn't this be using the crew size set in the Pulse project? Or is this not part of phase 1? This needs to be investigated. Creating this ticket for documenting findings. | Bug | In Development | In Progress | Medium | MCIS | SD-WAN | Klemetsen, Lene Mari | Giskegjerde, Trond Vidar | 2026-09-18 07:20 | 2026-10-13 00:18 | 26 | 2 |  | MCIS, OMS |  | NA | NA |  | https://jira.viasat.com/browse/SDWAN-13446
SDWAN-13474 | Some assurance data metrics from the VS60 are 0 | The following metrics were observed as 0 values: AZIMUTH ELEVATION LATITUDE LATITUDECOMPASSVALUE LONGITUDE LONGITUDECOMPASSVALUE SATELLITELONGITUDE SATELLITELONGITUDECOMPASSVALUE ANTTENNATEMP | Bug | In QA | In Progress | Medium | R4.4.1 | SD-WAN | Smith, Nick | Smith, Nick | 2026-09-21 06:16 | 2026-10-07 00:34 | 23 | 8 |  | R4.4.1, VS3-Beta |  | r4.4.1 | R4.4 |  | https://jira.viasat.com/browse/SDWAN-13474
SDWAN-13585 | sdwan-activation-service SeedDefinedConsumer drops sdwan-seed-data-defined on transient seed-generator errors - seed data never stored | h3. Summary When {{SeedDefinedConsumer}} in sdwan-activation-service ({{db_updater}}) receives {{inmarsat.product-core.configuration.networking.sdwan-seed-data-defined}}, it calls seed-generator {{GET /v1/seep/link-inventory/<sdp_id>}} to fetch the seed ISO S3 link. If that call fails, the task raises {{InternalError}} and the message is lost. The message is published with {{delivery_mode NOT_PERSISTENT}}, and there is no retry, requeue or dead-letter. The activation service never stores seed data for that SDP. h3. Evidence (dev, SDP 250000000105400, 2026-09-26) Jaeger span chain: {{[SeedDefinedConsumer] Handle Message Task}}, then {{Get Seed Data Firmware S3 Link}} (InternalError), then {{_get_json_data}} (HTTPError), then {{GET http://sdwan-seed-generator.sdwan-manager.svc.cluster.local/v1/seep/link-inventory/250000000105400}} (ConnectTimeout after 5s). The seed generator had already uploaded {{seed-250000000105400.iso}} to S3 successfully. Later, a {{/manifest}} request for that... | Bug | New | To Do | Medium | R4.5 | SD-WAN | Unassigned | Holder, Joe | 2026-09-27 00:16 | 2026-09-27 00:16 | 18 | 18 |  | sdwan-activation-service, slowtrack |  |  | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13585
SDWAN-13678 | CircleCI unit test jobs show as passed even when tests fail | *Problem* Some services run their unit tests through a {{run_unit_tests.sh}} script that only fails the job if code coverage drops too low. If a test fails but coverage is still above the threshold, the CircleCI job stays green, so broken tests go unnoticed. *Found in* fleet_edge_updater: 2 unit tests have been failing on master on both the current and next streams, while CircleCI showed {{unit_test}} / {{unit_test_next}} as passed. Found while working on the Alpine 3.23 promotion (DORA-6818, PR on branch DORA-6818). *Fix* Add {{set -e}} to the top of the test script so any failing test fails the job, then fix any tests this exposes. *Services* ¦¦ Service ¦¦ Status ¦¦ ¦ fleet_edge_updater ¦ Affected (2 hidden failures). Fix + test corrections in the DORA-6818 PR ¦ ¦ fleet_edge_bootstrap_mgmt ¦ Affected script, no hidden failures today. Needs {{set -e}} ¦ ¦ fleet_edge_secrets_scheduler ¦ Already fixed (secrets-scheduler PR #56) ¦ ¦ pandora_edge_bootstrap, pandora_edge_security_valida... | Bug | Code Review | In Progress | Medium | R4.5 | SD-WAN | Vailamur Nagarajan, Koushal | Vailamur Nagarajan, Koushal | 2026-10-09 03:01 | 2026-10-13 00:47 | 5 | 2 |  | Inlife |  | R4.5 | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13678
SDWAN-13687 | lab_250_deploy_edge_image fails on older FE images: reenable_eth0.py assumes 'auto UNDERLAY00' exists in /etc/network/interfaces | h3. Summary Deploying an older Fleet Edge image (e.g. *2.3.176.3153-master*) via Jenkins job *lab_250_deploy_edge_image* fails in stage *"Await reboot. Re-enable eth0. Verify"*. Imaging itself succeeds; the failure is in {{common/pandora/reenable_eth0.py}}, which assumes the newer image's {{/etc/network/interfaces}} layout. Reproduced on more than one lab edge; build #160597 on *edge-bur-015* analysed below. h3. Background Old images are stored in S3 bucket {{product-common-ew1-buildartefacts}} ({{fleet-edge/images/}}) under *Intelligent-Tiering* and move to *Deep Archive Access* after ~180 days without access. Before deploying, they must be restored (S3 console -> Object actions -> Initiate restore, Standard, up to ~12h; needs a role with {{s3:RestoreObject}} — {{view}} role is insufficient). Otherwise {{pull_and_reboot.py}} fails with {{InvalidObjectState ... not valid for the object's access tier}} (seen on edge-ldn-044 with 2.3.318.3420-master). After restore, the download in #1... | Bug | Code Review | In Progress | Medium | R4.5 | SD-WAN | Vailamur Nagarajan, Koushal | Vailamur Nagarajan, Koushal | 2026-10-11 10:42 | 2026-10-13 22:48 | 3 | 1 |  | Inlife |  | R4.5 | 26.4 |  | https://jira.viasat.com/browse/SDWAN-13687
SDWAN-13717 | Bootstrap not possible | Failing on C5921 {code:java} IMAGE_VERSION: 2.16.443 LAYER_VERSION: NOT_SET ***THERE IS A NEW VAR PASSWORD*** 10-14 08:37:55.354 CNS ¦ UID: 10-14 08:37:55.388 CNS ¦ CNS ID: 10-14 08:37:55.423 CNS ¦ NSD ID: 10-14 08:37:55.459 CNS ¦ Software Version: 2.16.443 10-14 08:37:55.493 CNS ¦ Software Layer Version: NOT_SET 10-14 08:37:55.527 CNS ¦ 10-14 08:37:55.561 CNS ¦ Checking if etcd service is running... 10-14 08:37:55.632 CNS ¦ Checking if c5921 VM is running... Current date/time: 2026-10-14 08:37:57 Do you want to reset the date and time? [y/N] n 10-14 08:38:21.792 CNS ¦ Please enter the site details. 10-14 08:38:21.828 CNS ¦ CNS ID wy5w75JOa1obUC4 10-14 08:38:27.333 CNS ¦ Accepted CNS ID: wy5w75JOa1obUC4 10-14 08:38:27.368 CNS ¦ CCE Instance 1 10-14 08:38:28.035 CNS ¦ Accepted CCE instance: 1 10-14 08:38:28.069 CNS ¦ Creating cnsfile... 10-14 08:38:28.106 CNS ¦ Configuring the C5921... 10-14 08:44:42.129 CNS ¦ ...failed. Return code:1. Aborting. 10-14 08:44:42.164 CNS ¦ Conn... | Bug | New | To Do | Medium | R4.5 | SD-WAN | Unassigned | Oien, Ole - Richard | 2026-10-14 01:54 | 2026-10-14 07:38 | 1 | 0 |  |  |  |  | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13717
DORA-6756 | boot-strap-management glitches sometimes and does not send mqtt data | Under investigation: Some times it seems like the boot-strap-management services glitches on mqtt. It just stop sending data on the mqtt stream and the log is empty after the reboot... The system continues the installation processes when it happen but the Retail installer is depending on "success/failure" on mqtt to know if it should start with the next step. | Bug | New | To Do | Low | R4.5 | Pandora | Unassigned | Oien, Ole - Richard | 2026-08-20 03:15 | 2026-08-20 03:17 | 55 | 55 |  | R4.5 |  |  |  |  | https://jira.viasat.com/browse/DORA-6756
SDWAN-13325 | Blockage zone active information incorrect | There is a method that should take a boolean value and return a string value. The issue is that the incoming value gets converted to upper case camel, so comparing true to True always returns false as a configured blockage zone. Ole, Stig and I agreed that this can be a 4.4.1 or a 4.5 and for VS3 Beta vessels, the latest of the vseacu is enough for this fix | Bug | In QA | In Progress | Low | R4.4.1 | SD-WAN | Smith, Nick | Smith, Nick | 2026-09-08 05:07 | 2026-10-07 00:34 | 36 | 8 |  | R4.4.1, VS3-Beta |  | r4.4.1 | R4.4 |  | https://jira.viasat.com/browse/SDWAN-13325
SDWAN-13586 | hosting-manager prelaunch-manifest rewraps every upstream activation-service HTTP error as 404, hiding the real cause from the edge | h3. Summary In {{hosting_manager/api/app/utils.py}}, {{get_download_links()}} catches {{requests.HTTPError}} from the sdwan-activation-service {{/manifest}} call and always raises {{HTTPException(status_code=404, detail="HTTP error occurred: ...")}}, whatever the upstream status was. It also drops the upstream {{detail}} body. As a result the edge's {{get_prelaunch_manifest.py}} only ever prints {{error 404 returned from prelaunch_manifest call}}. h3. Evidence (dev, 2026-09-26, SDP 250000000105400) All of the following came back to the edge as a plain 404: * Upstream 404 {{ValidationError - seed data not found for sdp_id='250000000105400'}} * Upstream 500 {{could not connect to database - DBError - Policy controller could not be created.}} * Upstream 500 {{DBError - Error reading seed data for a given sdp_id}} The seep_activation Ansible output only showed "error 404 ... Missing ISO File". Finding the real cause needed the hm-api Jaeger spans, which slowed down triage of the lab_356... | Bug | New | To Do | Low | R4.5 | SD-WAN | Unassigned | Holder, Joe | 2026-09-27 00:16 | 2026-09-27 00:16 | 18 | 18 |  | hosting-manager, slowtrack |  |  | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13586

## VS3
Key | Summary | Description | Type | Status | Status Category | Priority | Matched Tags | Project | Assignee | Reporter | Created | Updated | Age (days) | Days Since Update | Due Date | Labels | Components | Fix Versions | Affects Versions | Parent | URL
QEGNS-2 | VS3 Reflector Tie Rod Weld Failure – Butt Joint Separation at Sleeve | Field failures observed where reflector tie rod butt welds at the sleeve are cracking/separating, compromising reflector structural integrity. Original supplier (Global Skyware) is out of business. Norcar Satcom acquired IP and continues sourcing from the same China supplier. *Action:* Implement supplier quality controls and weld validation with Norcar Satcom prior to procuring replacement tie rods for field remediation. | Bug | SME Review | In Progress | Medium | VS3 | Quality Engineering - Global Ground Network Systems | McGuinness, Jack | McGuinness, Jack | 2026-02-16 10:10 | 2026-09-29 12:23 | 240 | 15 |  | VS3 |  |  |  |  | https://jira.viasat.com/browse/QEGNS-2
SDWAN-12614 | Submitting an invalid VS3 MAC address causes SDP order to get stuck and not allowing new order with corrected MAC | If you specify wrong MAC address in Pulse you will not get any notifications that it's wrong before "it's too late". SDP will try to provision the CDQ with the invalid MAC and attach this to the current CNS ID or Remote site ID. The SDP order get stuck in running state but also left in a state where it cannot be aborted, since it's already sent this to CDQ. This is what I see when checking the status in SDP web interface: !image-2026-06-04-10-58-35-678.png¦width=307,height=407! In Pulse I only see the order is "failed". This error message should have given an explanation of why it failed. We need to investigate what happened here. After correcting the MAC address, I re-submitted the provision VS3 request. Then I got this error: {code:java} Failed : One or more previous messages with ids ae30b916-fbce-4bed-8c72-203b129e4eaa related to site_id 127744 are still being handled. Please wait for them to complete and then try your request again. {code} If an invalid MAC address is specified... | Bug | In QA | In Progress | Medium | VS3 | SD-WAN | Shrewsbury, Federico | Giskegjerde, Trond Vidar | 2026-06-04 01:58 | 2026-08-20 03:30 | 133 | 55 |  | VS3 |  | PI 26.2, 26.3 | NA |  | https://jira.viasat.com/browse/SDWAN-12614

## MCIS
Key | Summary | Description | Type | Status | Status Category | Priority | Matched Tags | Project | Assignee | Reporter | Created | Updated | Age (days) | Days Since Update | Due Date | Labels | Components | Fix Versions | Affects Versions | Parent | URL
SDWAN-13229 | MCIS, AISM Ubuntu VM requires reboot to enable VLAN20 | The Ubuntu version of the AISM VM is setup with vlan201 as default. When MICS is activated, VLAN201 is removed from the network interface file, and VLAN20 is added. But the change is not automatically applied. To get it working, it's required to manually reboot the AISM VM to get CrewHub service working. The Value added services projects do not have any tasks for doing this, and in my opinion, adding a task for doing a reboot is not the way to go when we want processes to be automated as much as possible. I assume there is a script or playbook pulling config from shore. Wouldn't it be able to detect interface changes and reboot the service if any changes are detected? | Bug | Code Review | In Progress | High | MCIS | SD-WAN | Holder, Joe | Giskegjerde, Trond Vidar | 2026-08-26 04:16 | 2026-09-17 06:45 | 49 | 27 |  | MCIS |  | 26.3 | NA |  | https://jira.viasat.com/browse/SDWAN-13229
SDWAN-13329 | hosting_manager: VM_NAME_TO_SDS_HOST still maps to 'mcis-aism' after SDWAN-13107 — running-version MDF never published | h3. Symptom hosting_manager was missed in the SDWAN-13107 rename sweep: {{api/app/endpoints.py:177}} still maps the agent-reported image name onto the retired trial host key {{mcis-aism}}. Consequently {{/v1/notify}} resolves no service for an AISM running-version report and skips the {{hosting-service-status-received}} MDF publish, warning-logged only. *Scope of impact, stated precisely:* * *No shore service consumes this message.* Grepped every repo in the Repos index — the only consumer is the SI harness. Nothing in production is degraded by it. * *SI_654's running-version scenario should be failing.* {{SI_654_mcis_coverage.feature:56}} binds a watcher and expects the MDF within 15 minutes, then asserts {{the reported host in the MDF message is "aism"}}. With nothing published that step times out. *Not yet run* — this is deduced from the code, and it is the check that would confirm or refute the whole diagnosis. If that scenario has been green since #171 merged, the diagnosis is... | Bug | Code Review | In Progress | High | MCIS | SD-WAN | Holder, Joe | Holder, Joe | 2026-09-09 02:13 | 2026-09-09 03:06 | 35 | 35 |  | PI-26.3-Planned-Committed, Value_adds_and_service_customisation | MCIS | 26.3 | 26.3 |  | https://jira.viasat.com/browse/SDWAN-13329
SDWAN-11453 | MCIS activation status in Pulse show success also when it failed | Issue found during MCIS integration testing. The MCIS activation status in Pulse only reflects if OMS are happy with the request or not. If it fails in AeroManager or SDWAN manager this is not shown anywhere. Due to this it will not be possible to see if MCIS activation is successful or not before the config is applied on the Edge and tested by customer. There must be an indication somewhere that MCIS activation has completed succesfully through all the involved systems. Preferrably in the status view for the MCIS activation in Pulse. !image-2025-12-05-15-50-51-810.png! | Bug | Triaged | To Do | Medium | MCIS | SD-WAN | Norris, Oliver | Giskegjerde, Trond Vidar | 2025-12-05 06:40 | 2026-06-02 01:45 | 313 | 135 |  | MCIS |  |  |  |  | https://jira.viasat.com/browse/SDWAN-11453
SDWAN-13444 | MCIS, Checkbox for manual FH deactivation not working | If Fleet Hotspot have been manually deactivated on a system, the checkbox for confirming this does not make any difference for MCIS. Even if ticked off it will display an error message about FH deprovision is required when I try to provision MCIS. !image-2026-09-18-16-06-59-753.png¦width=623,height=1490! | Bug | Code Review | In Progress | Medium | MCIS | SD-WAN | Giskegjerde, Trond Vidar | Giskegjerde, Trond Vidar | 2026-09-18 07:08 | 2026-10-08 01:28 | 26 | 7 |  | MCIS |  | PI 26.3 | NA |  | https://jira.viasat.com/browse/SDWAN-13444
SDWAN-13446 | MCIS, Crew size is hardcoded to 64 in OMS template | Currently, the crew size has been hardcoded to 64 in the MCIS template in OMS. Shouldn't this be using the crew size set in the Pulse project? Or is this not part of phase 1? This needs to be investigated. Creating this ticket for documenting findings. | Bug | In Development | In Progress | Medium | MCIS | SD-WAN | Klemetsen, Lene Mari | Giskegjerde, Trond Vidar | 2026-09-18 07:20 | 2026-10-13 00:18 | 26 | 2 |  | MCIS, OMS |  | NA | NA |  | https://jira.viasat.com/browse/SDWAN-13446

## R4.5
Key | Summary | Description | Type | Status | Status Category | Priority | Matched Tags | Project | Assignee | Reporter | Created | Updated | Age (days) | Days Since Update | Due Date | Labels | Components | Fix Versions | Affects Versions | Parent | URL
SDWAN-13395 | Geo-Fencing SNAPI Interface unstable | It seems snapi interface is not as stable as it used to be. The snapi calls are synchronous and are intertwined with async code. My hunch is that when we retry to connect to SNAPI everything waits for that to finish. It also happens in dev, CI tests are failing randomly because of this if I remember correctly from the last time I checked with Dinu | Bug | In Development | In Progress | High | R4.5 | SD-WAN | Radu, George (Contractor) | Holder, Joe | 2026-09-15 07:21 | 2026-10-07 01:08 | 29 | 8 |  | R4.5 |  | 26.3, R4.5 | 26.3 |  | https://jira.viasat.com/browse/SDWAN-13395
SDWAN-13584 | sdwan-seed-generator API container has no readiness/liveness probe - hung gunicorn worker went undetected for 2.5 days on dev | h3. Summary On dev, the sdwan-seed-generator REST API stopped serving at 2026-09-24 18:36 UTC and stayed that way until it was manually restarted on 2026-09-27 07:13 UTC. Kubernetes kept reporting the pod as 2/2 Running/Ready the whole time, because the {{sdwan-seed-generator-api}} container has no readiness or liveness probe. h3. Evidence * Pod {{sdwan-seed-generator-deployment-db5468c48-llqnq}}, created 18:33 UTC Thu as a replacement pod. The previous pod and a parameter-manager pod were left stuck Terminating on node ip-10-200-74-222, which suggests a node disruption. * gunicorn config: 1 worker, sync worker class, 1 thread, bind 0.0.0.0:80. The container log ends at "1 workers" and never shows "Booting worker with pid". Worker process 17 was alive but served nothing. * {{GET http://127.0.0.1:80/v1/seep/link-inventory/<sdp>}} run *inside the pod* timed out. From sdwan-activation-service, both the Service DNS name and the pod IP gave ConnectTimeout. * After {{kubectl rollout resta... | Bug | In QA | In Progress | High | R4.5 | SD-WAN | Holder, Joe | Holder, Joe | 2026-09-27 00:16 | 2026-10-05 07:45 | 18 | 9 |  | sdwan-seed-generator, slowtrack |  | 26.4 | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13584
DORA-6822 | Hosting will not start. | Vessel Name: Elandra Cypress Remote Site ID: 250100324550000 CNSID: QlqULO70mYK8d4u CCE Instance: 2 It seems to be affected [https://jira.viasat.com/browse/SDWAN-11528] and in additional crashed the environment. Have added the CPU shares again, they was missing int the conf.d and init.d file. Did also copy the whole conf.d file and init.d file from a working R4.4 system since the container version was the same, no effect. ( both old files are present as .bak {code:java} docker logs hosting exec /entrypoint.sh: exec format error {code} {code:java} drwxr-xr-x 2 root root 4096 Dec 11 2025 _data -rw------- 1 root root 101 Dec 11 2025 opts.json /var/lib/docker/volumes/hosting-var_images # cd _data/ /var/lib/docker/volumes/hosting-var_images/_data # ls -l total 0 {code} {code:java} sudo service hosting start hosting * Starting hosting ... * All interfaces are available: eth4 eth9 RTNETLINK answers: File exists RTNETLINK answers: File exists de790501a3e3e2376344929ad3534610f249e09ce385... | Bug | In Development | In Progress | High | R4.5 | Pandora | Vailamur Nagarajan, Koushal | Oien, Ole - Richard | 2026-09-29 01:21 | 2026-10-13 22:50 | 16 | 1 |  | Inlife, R4.5 |  | R4.5 |  |  | https://jira.viasat.com/browse/DORA-6822
DORA-6864 | Updater 1.0.78 cannot SSH to c5921, remote upgrade fails after reboot | *Problem* After the updater moved to Alpine 3.23 (fleet_edge_updater PR #177, updater 1.0.78), remote upgrades are marked FAILED after the edge reboots. The upgrade itself completes, but the updater's post-reboot "edge is fully up" check times out. Seen in Slow Track (build 2.16.512): SI-582 (pull remote upgrade) and SI-584 (two-stage remote upgrade). *Cause* The check SSHes from the updater container to each edge host, including c5921. The new image has OpenSSH 10.2, which no longer accepts the legacy SSH algorithms c5921 uses (ssh-rsa host key and RSA certificate login). The old image (OpenSSH 8.1) accepted them. {noformat}Unable to negotiate with 10.0.3.8 port 22: no matching host key type found. Their offer: ssh-rsa,ssh-dss{noformat} *Fix* Re-enable the legacy algorithms in the updater image for c5921 only (same options as the SI fix in SDWAN-12955): {noformat}HostKeyAlgorithms +ssh-rsa PubkeyAcceptedAlgorithms ssh-rsa-cert-v01@openssh.com,ssh-rsa{noformat} Verified manually on... | Bug | In Development | In Progress | High | R4.5 | Pandora | Vailamur Nagarajan, Koushal | Vailamur Nagarajan, Koushal | 2026-10-11 07:56 | 2026-10-11 20:17 | 3 | 3 |  | Inlife | edge-updater, remote-upgrade | R4.5 |  |  | https://jira.viasat.com/browse/DORA-6864
DORA-6868 | Updater 1.0.78 lacks Ansible collections: all_targets.yaml fails to load, so the remote upgrade fails 2 s after precache | h3. Problem Since updater 1.0.78 (fleet_edge_updater PR #177, DORA-6818: current moved to Alpine 3.23 / ansible-core 2.19), a remote upgrade fails on any edge that is running the new updater. Precache succeeds, then {{all_targets.yaml}} fails to load. About 2 seconds later the transaction goes to PLAYBOOK_EXECUTION_FAILED, with no task output and an empty reason. The image installs ansible-core (built-in modules only) plus {{community.docker}}. That covers {{precache_edge.yaml}} ({{docker_image}}), but fleet_edge_provisioning also uses modules from other collections: ¦¦Collection¦¦Modules used¦¦Effect¦¦ ¦community.general¦modprobe, lvg, lvol, filesystem, influxdb_database, influxdb_retention_policy¦all_targets.yaml fails to load (modprobe in roles/common/tasks/main.yaml:81)¦ ¦ansible.posix¦ansible.builtin.mount / mount (provision_network.yaml, provision_core.yaml)¦all_targets.yaml fails to load¦ ¦community.libvirt¦virt, virt_net (roles/libvirt, roles/vms/tasks/*_upgrade.yaml, cleanu... | Bug | In Development | In Progress | High | R4.5 | Pandora | Holder, Joe | Varatharajah, Gobeeshan | 2026-10-13 01:37 | 2026-10-13 07:41 | 2 | 1 |  | Inlife, claude-code-support |  | R4.5 |  |  | https://jira.viasat.com/browse/DORA-6868
SDWAN-9929 | Netmon monitoring of eth7 and eth8 doesn't work | Monitoring of eth7 and eth8 does not work. See error in log below. Also, if I shutdown eth7 and eth8 manually they will not be taken up by the netmon service again. For eth6 it works fine. Docker logs netmon: {noformat}* 2025-08-01 12:53:55 [ INFO ] [ state_machine.py (41)¦ state_machine - (Thread-1) ] :: State::process_state() * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (43)¦ state_machine - (Thread-1) ] :: State::process_state() state: NetmonState.ALL_INTERFACES_UP * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (70)¦ state_machine - (Thread-1) ] :: State::process_state() iterating managed interfaces: ['eth1', 'eth2', 'eth6', 'eth7, eth8'] * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (72)¦ state_machine - (Thread-1) ] :: State::process_state() checking if interface eth1 is down * 2025-08-01 12:53:55 [ INFO ] [ eth_handler.py (11)¦ eth_handler - (Thread-1) ] :: is_interface_down(eth1) False * 2025-08-01 12:53:55 [ DEBUG ] [ state_machine.py (72)¦ state... | Bug | Code Review | In Progress | Medium | R4.5 | SD-WAN | Holder, Joe | Giskegjerde, Trond Vidar | 2025-08-01 05:58 | 2026-10-07 08:53 | 439 | 7 |  | Inlife, R4.5 | netmon | 26.4 |  |  | https://jira.viasat.com/browse/SDWAN-9929
DORA-6764 | DORA-6751 follow-up: harden c5921 against analogous NIC identity/enumeration exposure | Follow-up to DORA-6751. The DORA-6751 fix (fleet_edge_provisioning PR [#1084¦https://github.com/Inmarsat/fleet_edge_provisioning/pull/1084], now merged) hardened the *network* and *core* VMs against the boot-time NIC-enumeration race by waiting for each MAC before {{nameif}}. It explicitly *descoped the c5921* ("Cisco IOS, different mechanism"). This ticket covers the c5921, which has an *analogous latent exposure* — and was in fact the variant seen on customer vessels in DORA-6751. h4. Correction to the original scoping note The c5921 is not a bare Cisco-IOS appliance. It is a KVM guest running a *CentOS/RHEL-family Linux* (uses {{/etc/sysconfig/network-scripts/ifcfg-*}}) that hosts the Cisco ESR software router as a userspace process. So it is Linux underneath and *does* have a NIC-identity story — just a different one from the Debian {{nameif}} VMs. h4. The exposure (code-grounded) Refs: {{fleet_edge_provisioning:roles/vms/templates/c5921/c5921.xml}}, {{roles/c5921/tasks/main.yam... | Bug | Ready for Sprint | To Do | Medium | R4.5 | Pandora | Holder, Joe | Holder, Joe | 2026-08-26 00:52 | 2026-08-26 03:58 | 50 | 49 |  | Inlife, R4.5 |  | PI 26.3 |  |  | https://jira.viasat.com/browse/DORA-6764
SDWAN-13585 | sdwan-activation-service SeedDefinedConsumer drops sdwan-seed-data-defined on transient seed-generator errors - seed data never stored | h3. Summary When {{SeedDefinedConsumer}} in sdwan-activation-service ({{db_updater}}) receives {{inmarsat.product-core.configuration.networking.sdwan-seed-data-defined}}, it calls seed-generator {{GET /v1/seep/link-inventory/<sdp_id>}} to fetch the seed ISO S3 link. If that call fails, the task raises {{InternalError}} and the message is lost. The message is published with {{delivery_mode NOT_PERSISTENT}}, and there is no retry, requeue or dead-letter. The activation service never stores seed data for that SDP. h3. Evidence (dev, SDP 250000000105400, 2026-09-26) Jaeger span chain: {{[SeedDefinedConsumer] Handle Message Task}}, then {{Get Seed Data Firmware S3 Link}} (InternalError), then {{_get_json_data}} (HTTPError), then {{GET http://sdwan-seed-generator.sdwan-manager.svc.cluster.local/v1/seep/link-inventory/250000000105400}} (ConnectTimeout after 5s). The seed generator had already uploaded {{seed-250000000105400.iso}} to S3 successfully. Later, a {{/manifest}} request for that... | Bug | New | To Do | Medium | R4.5 | SD-WAN | Unassigned | Holder, Joe | 2026-09-27 00:16 | 2026-09-27 00:16 | 18 | 18 |  | sdwan-activation-service, slowtrack |  |  | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13585
SDWAN-13678 | CircleCI unit test jobs show as passed even when tests fail | *Problem* Some services run their unit tests through a {{run_unit_tests.sh}} script that only fails the job if code coverage drops too low. If a test fails but coverage is still above the threshold, the CircleCI job stays green, so broken tests go unnoticed. *Found in* fleet_edge_updater: 2 unit tests have been failing on master on both the current and next streams, while CircleCI showed {{unit_test}} / {{unit_test_next}} as passed. Found while working on the Alpine 3.23 promotion (DORA-6818, PR on branch DORA-6818). *Fix* Add {{set -e}} to the top of the test script so any failing test fails the job, then fix any tests this exposes. *Services* ¦¦ Service ¦¦ Status ¦¦ ¦ fleet_edge_updater ¦ Affected (2 hidden failures). Fix + test corrections in the DORA-6818 PR ¦ ¦ fleet_edge_bootstrap_mgmt ¦ Affected script, no hidden failures today. Needs {{set -e}} ¦ ¦ fleet_edge_secrets_scheduler ¦ Already fixed (secrets-scheduler PR #56) ¦ ¦ pandora_edge_bootstrap, pandora_edge_security_valida... | Bug | Code Review | In Progress | Medium | R4.5 | SD-WAN | Vailamur Nagarajan, Koushal | Vailamur Nagarajan, Koushal | 2026-10-09 03:01 | 2026-10-13 00:47 | 5 | 2 |  | Inlife |  | R4.5 | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13678
SDWAN-13687 | lab_250_deploy_edge_image fails on older FE images: reenable_eth0.py assumes 'auto UNDERLAY00' exists in /etc/network/interfaces | h3. Summary Deploying an older Fleet Edge image (e.g. *2.3.176.3153-master*) via Jenkins job *lab_250_deploy_edge_image* fails in stage *"Await reboot. Re-enable eth0. Verify"*. Imaging itself succeeds; the failure is in {{common/pandora/reenable_eth0.py}}, which assumes the newer image's {{/etc/network/interfaces}} layout. Reproduced on more than one lab edge; build #160597 on *edge-bur-015* analysed below. h3. Background Old images are stored in S3 bucket {{product-common-ew1-buildartefacts}} ({{fleet-edge/images/}}) under *Intelligent-Tiering* and move to *Deep Archive Access* after ~180 days without access. Before deploying, they must be restored (S3 console -> Object actions -> Initiate restore, Standard, up to ~12h; needs a role with {{s3:RestoreObject}} — {{view}} role is insufficient). Otherwise {{pull_and_reboot.py}} fails with {{InvalidObjectState ... not valid for the object's access tier}} (seen on edge-ldn-044 with 2.3.318.3420-master). After restore, the download in #1... | Bug | Code Review | In Progress | Medium | R4.5 | SD-WAN | Vailamur Nagarajan, Koushal | Vailamur Nagarajan, Koushal | 2026-10-11 10:42 | 2026-10-13 22:48 | 3 | 1 |  | Inlife |  | R4.5 | 26.4 |  | https://jira.viasat.com/browse/SDWAN-13687
SDWAN-13717 | Bootstrap not possible | Failing on C5921 {code:java} IMAGE_VERSION: 2.16.443 LAYER_VERSION: NOT_SET ***THERE IS A NEW VAR PASSWORD*** 10-14 08:37:55.354 CNS ¦ UID: 10-14 08:37:55.388 CNS ¦ CNS ID: 10-14 08:37:55.423 CNS ¦ NSD ID: 10-14 08:37:55.459 CNS ¦ Software Version: 2.16.443 10-14 08:37:55.493 CNS ¦ Software Layer Version: NOT_SET 10-14 08:37:55.527 CNS ¦ 10-14 08:37:55.561 CNS ¦ Checking if etcd service is running... 10-14 08:37:55.632 CNS ¦ Checking if c5921 VM is running... Current date/time: 2026-10-14 08:37:57 Do you want to reset the date and time? [y/N] n 10-14 08:38:21.792 CNS ¦ Please enter the site details. 10-14 08:38:21.828 CNS ¦ CNS ID wy5w75JOa1obUC4 10-14 08:38:27.333 CNS ¦ Accepted CNS ID: wy5w75JOa1obUC4 10-14 08:38:27.368 CNS ¦ CCE Instance 1 10-14 08:38:28.035 CNS ¦ Accepted CCE instance: 1 10-14 08:38:28.069 CNS ¦ Creating cnsfile... 10-14 08:38:28.106 CNS ¦ Configuring the C5921... 10-14 08:44:42.129 CNS ¦ ...failed. Return code:1. Aborting. 10-14 08:44:42.164 CNS ¦ Conn... | Bug | New | To Do | Medium | R4.5 | SD-WAN | Unassigned | Oien, Ole - Richard | 2026-10-14 01:54 | 2026-10-14 07:38 | 1 | 0 |  |  |  |  | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13717
DORA-6756 | boot-strap-management glitches sometimes and does not send mqtt data | Under investigation: Some times it seems like the boot-strap-management services glitches on mqtt. It just stop sending data on the mqtt stream and the log is empty after the reboot... The system continues the installation processes when it happen but the Retail installer is depending on "success/failure" on mqtt to know if it should start with the next step. | Bug | New | To Do | Low | R4.5 | Pandora | Unassigned | Oien, Ole - Richard | 2026-08-20 03:15 | 2026-08-20 03:17 | 55 | 55 |  | R4.5 |  |  |  |  | https://jira.viasat.com/browse/DORA-6756
SDWAN-13586 | hosting-manager prelaunch-manifest rewraps every upstream activation-service HTTP error as 404, hiding the real cause from the edge | h3. Summary In {{hosting_manager/api/app/utils.py}}, {{get_download_links()}} catches {{requests.HTTPError}} from the sdwan-activation-service {{/manifest}} call and always raises {{HTTPException(status_code=404, detail="HTTP error occurred: ...")}}, whatever the upstream status was. It also drops the upstream {{detail}} body. As a result the edge's {{get_prelaunch_manifest.py}} only ever prints {{error 404 returned from prelaunch_manifest call}}. h3. Evidence (dev, 2026-09-26, SDP 250000000105400) All of the following came back to the edge as a plain 404: * Upstream 404 {{ValidationError - seed data not found for sdp_id='250000000105400'}} * Upstream 500 {{could not connect to database - DBError - Policy controller could not be created.}} * Upstream 500 {{DBError - Error reading seed data for a given sdp_id}} The seep_activation Ansible output only showed "error 404 ... Missing ISO File". Finding the real cause needed the hm-api Jaeger spans, which slowed down triage of the lab_356... | Bug | New | To Do | Low | R4.5 | SD-WAN | Unassigned | Holder, Joe | 2026-09-27 00:16 | 2026-09-27 00:16 | 18 | 18 |  | hosting-manager, slowtrack |  |  | R4.5 |  | https://jira.viasat.com/browse/SDWAN-13586

## R4.4.1
Key | Summary | Description | Type | Status | Status Category | Priority | Matched Tags | Project | Assignee | Reporter | Created | Updated | Age (days) | Days Since Update | Due Date | Labels | Components | Fix Versions | Affects Versions | Parent | URL
SDWAN-13436 | VS3 ACU assurance data check is incorrect | When we first developed against the Intellian VS60, we only had a simulator to work with to get assurance data, and there is a check in the code to validate metrics before we can save them to disk. We took this code out but when doing so, the underlying logic was wrong. | Bug | In QA | In Progress | High | R4.4.1 | SD-WAN | Smith, Nick | Smith, Nick | 2026-09-18 03:22 | 2026-10-07 00:34 | 26 | 8 |  | R4.4.1, VS3-Beta |  | r4.4.1 | R4.4 |  | https://jira.viasat.com/browse/SDWAN-13436
SDWAN-13474 | Some assurance data metrics from the VS60 are 0 | The following metrics were observed as 0 values: AZIMUTH ELEVATION LATITUDE LATITUDECOMPASSVALUE LONGITUDE LONGITUDECOMPASSVALUE SATELLITELONGITUDE SATELLITELONGITUDECOMPASSVALUE ANTTENNATEMP | Bug | In QA | In Progress | Medium | R4.4.1 | SD-WAN | Smith, Nick | Smith, Nick | 2026-09-21 06:16 | 2026-10-07 00:34 | 23 | 8 |  | R4.4.1, VS3-Beta |  | r4.4.1 | R4.4 |  | https://jira.viasat.com/browse/SDWAN-13474
SDWAN-13325 | Blockage zone active information incorrect | There is a method that should take a boolean value and return a string value. The issue is that the incoming value gets converted to upper case camel, so comparing true to True always returns false as a configured blockage zone. Ole, Stig and I agreed that this can be a 4.4.1 or a 4.5 and for VS3 Beta vessels, the latest of the vseacu is enough for this fix | Bug | In QA | In Progress | Low | R4.4.1 | SD-WAN | Smith, Nick | Smith, Nick | 2026-09-08 05:07 | 2026-10-07 00:34 | 36 | 8 |  | R4.4.1, VS3-Beta |  | r4.4.1 | R4.4 |  | https://jira.viasat.com/browse/SDWAN-13325